## Slide 1: Project Genesis Plus Re-engineer data flows into Snowflake and enable self-service Project Kickoff Presentation
November 8, 2022

## Slide 2: Project Genesis Plus - Agenda
Data & Analytics – Vision & Strategic Priorities
Project Background & Problem Statement
Project Charter
Project Team
Solution Approach & Architecture
Project Tracks
  Data Domain Track Approach
  Consumption & Self-Service Track Approach
Schedule & Milestones
Appendix
  Project Management - Agile
  Risk Management Process
  Communication & Meetings Cadence

## Slide 3
Business driven strategy & operating model to drive business value and innovation
Organization, processes & tools to govern enterprise data lifecycle, data quality, business definitions, KPI’s & metrics
Modern Data platform and consumption tools that simplifies data ingestion, enrichment, management and consumption
Enable data driven decisions across HoT through increased awareness, reliable and accurate data, modern data platforms and easy to use tools for self-service
Strategy,& Operating Model
Governance & Management
Platforms and Tools
Helen of Troy Data & Analytics – Vision & Strategic Priorities
Empower business to use governed self-service for business analytics – SC, Finance, Consumer, IoT, POS and other domains
Business Analytics & Self-Service
Raise data culture awareness through targeted training and ongoing engagement programs for all data stakeholders
Data Literacy & Culture
DATA
INFORMATION
KNOWLEDGE
WISDOM
Notes: 5 foundational pillars, to achieve our goal, we need to make relative progress on all 5, because each of them are important and intersect
with each other.
All our projects and initiatives should fit one of these pillars

## Slide 4
Can't self-serve or use for Adhoc needs
Self-Service Needs
Cannot drill down to detailed level for decision making
Drill-down Capability
Lack of Data Quality & ABC (Audit, Balance, Control)
Data Trust
Lack of HoT standard definitions, metrics, & KPI’s
Definition / KPI’s
Can't scale for performance, and different types of data
Scalability
Takes too long to bring new data in – POS, Competition, Weather, etc.
External Data Integration
Project Genesis Plus – Background & Problem Statement
The current Oracle Data Platform cannot fulfill our vision to enable data driven decisions at all levels and increase data maturity across Helen of Troy.

## Slide 5
Executive Summary | 
Phase 1 – Replicate Oracle EDW into Snowflake - Live Workstream 1 – Data replication and data pipelines are completed Workstream 2 - UAT with ~175 business users is complete across EMEA, H&W, H&O, Beauty & SS Workstream 3 ETL tool selection, as well as phase 2 design, roadmap are complete We are live as of August and all reports and dashboard are driven from Snowflake Genesis Plus- Migrate, sunset Oracle EDW & enable self-service Data Domain Track – Build new data pipelines from all HoT internal and external sources into Snowflake Consumption Models & Self-Service – Define HoT Level measures, metrics, business definitions, KPI’s and implement in Snowflake for self-service consumption | 
Project Genesis
FY23 |  |  |  |  |  |  |  |  | FY24 | FY24 | 
Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  | 
June | July | August | September | October | November | December | January | February | March | April | May
STATUS |  | 
Business Objective |  | 
Implement Snowflake as the next generation HoT Data Platform Phase 1 - Replicate Oracle EDW into Snowflake Genisus Plus - Rationalize, migrate, sunset Oracle EDW investments & enable self service |  | 
Executive Sponsor |  | 
Harish Ramani |  | 
Project Management |  | 
Gayle Isles Rick Seiden | Gayle Isles | 
Business Stakeholders |  | 
All divisions, departments | Data Leadership Council Members | Raj Kasbekar
Project Team |  | 
Information Delivery Team – Sai, Venkat, Derek, Mel, Balaji |  | 
3 Onsite Consultants |  | 
10 Offshore Consultants |  | 
Key Next Steps | 
Legal approval, and sign-offs for products & services Interview team members Project Kick-off Genesis Plus Team Onboarding & team training Design sign-off & Backlog Refinement | 
Key Risks / Issues & Resolution | 
❕ RISK: Dependency on external resources Mitigation: Interview each resource and use of multiple agencies ❕ RISK: Budget needs in FY24 Mitigation: Completion dependent on appropriate budget allocations in FY24 | 
Project Genesis Phase 1
Kick-off
Project Genesis Plus
Design
UAT
Go-Live
Dev
Kick-off
Design
UAT
Go-Live
Development
Prep

## Slide 6
Business (BU / Shared Service)
Delivery Team
Genesis Plus – Team/Org Structure
Architecture & Design
Aditya Gondesi
Pablo Marotta
Venkat Marakala
Engagement Sponsor
Harish Ramani
Product Owner
Sai Pedditi
Balaji Srinivasan
Project Manager / Scrum Master
Rick Seiden
Orders To Cash
Alice Starliper, Lory Vasquez
Monica Saenzpardo
Finance
Edgar Hernandez, Hugo Olivares, Kevin Richardson, Vincent Martinez
Procure To Pay
Romeo Chen, Jerri Bossie
Sherri Crawford, Edlyn Soler, Michelle Ortiz
User Acceptance Tester(s)
TBD
Data Engineering
Gurpreet Singh,
Priyanka Meshram
Vinod Kumar
Venkat Marakala
Pradhnya Shahu
Open (2)
Business Analysts
Mel Blizzard
Derek Spear
Steering Committee
Tracy Scheuerman, Aloke Mishra, Marisol Ayala, Matt Dunn, H&W - TBD, Craig Antolik, Harish Ramani, Anil Johnson, Balaji Srinivasan
PMO
Gayle Isles
Balaji Srinivasan
Sai Pedditi
Project Team
Report Developers
Shivaram Kolla
Lakshmi Narayana
QA
Srinivas Maram
Neha Jain
Data Leadership Council
Eric Proctor, Mike Burke, Gerritt Dewitt, Mike Wallenfels, Kirsten Augustad, Chris Fluhr, Brad Higginbotham, Anil Johnson, Tracy Scheuerman, Harish Ramani, Craig Antolik, Paul DeSousa, Melissa Allred, Melissa Villalon, Aloke Mishra
Logistics
Cedric Turnage, Moises Corral, Tonya Oliver
Notes: Merge into a vertical view

## Slide 7: Genesis Plus Architecture
Ad-hoc
Current Tools
Data Exchange
Transformation
System Source
Extraction & Loading
Project Genesis – Snowflake Implementation
Future Tools
* Represents currently available data & tools
Self Service Consumption Models
Business Self Service
  Data Domain Track - Build new data pipelines from all HoT internal and external sources into Snowflake
  Consumption & Self-Service Track – Define & implement measures, metrics, definitions, KPI’s for self-service

## Slide 8: Project Genesis - Solution Approach – Current State, Phase 1 and Phase 2
On-premise ( Oracle ODI, Oracle DW, OBIEE)
Stage
OLTP
Databases
Enterprise
Applications
Reporting Tools
Pre Genesis
Genesis Phase 1
Genesis Plus
Stage
EDW
EDW
OLTP
Databases
Enterprise
Applications
Reporting Tools
Snowflake
ODS/Stage
Sales Data Mart
OLTP
Databases
Enterprise
Applications
EDW
Operations Data Mart
Planning & Forecast Data Mart
Financial Data Mart
On-Cloud (Matillion ELT, Snowflake / Redshift EDW)
Reporting Tools
Snowflake
Snowflake
EDW
Snowflake

## Slide 9: Project Genesis - Solution Approach – Current State, Phase 1 and Phase 2
On-premise ( Oracle ODI, Oracle DW, OBIEE)
Stage
OLTP
Databases
Enterprise
Applications
Reporting Tools
Pre Genesis
Genesis Plus
ODS/Stage
Sales Data Mart
OLTP
Databases
Enterprise
Applications
EDW
Operations Data Mart
Planning & Forecast Data Mart
Financial Data Mart
On-Cloud (Matillion ELT, Snowflake / Redshift EDW)
Reporting Tools
Snowflake
Snowflake
EDW
Snowflake

## Slide 10
Requirements & Design
Reengineer Data ingestion
Build & Unit Test Data Pipeline
Orchestrate Data Jobs
User Acceptance Testing
Documentation & Deployment
Master Data
Finance
Orders to Cash
Procure to Pay
Logistics
Data Domain Validation & Testing
Project Genesis Plus – Data Domain Track
Track Activities
All data flows that supports our enterprise Oracle BI and Power BI reporting are being reengineered during this phase, to ensure data accuracy, we need validation and testing of key enterprise reports and dashboards
Product, Customer
AP, AR, GL, Accounting, Tax, Planning, Fixed Assets etc.
Order Management, CRM, Sales Operations, EDI etc.
Supply Planning, Demand Planning, Procurement
Sourcing, Distribution, Transportation
Notes: Define Integrated Business Teams, grouped by domain / function
Define HoT & BU level definitions, measures, metrics, & KPI’s
Implement the aligned definitions in Snowflakes Semantic layer
Roll-out self-service in iterative manner

## Slide 11: Genesis Plus – Data Domain Track Monthly UAT Approach
~330 total reports will be tested, monthly breakdown TBD
~85 UAT users are expected, monthly breakdown TBD
Testers will identified & given three-week lead time to start testing
Monthly UAT will typically last one week
We expect about two hours of testing each month for each tester
Monthly UAT starts in Dec and ends in May
Identify UAT Testers
Communicate Testing Timelines to Testers
Domain Users Commence Testing
Domain Users Report Any Bugs
Bugs Addressed
Domain Users Tests Again
Domain User Sign-off
Monthly UAT Approach
Notes: Who, when, how long how do we engage, what are they expected to do??

## Slide 12
Business Led & IT Supported
Align on Function Areas
Alignment
Functional Leads & Team
Identify
Consumption Models & Self-Service Approach
Approval by the DLC team members
Approval
5
7
Self-Service
Power BI & other tools
Implementation
Semantic Layer Snowflake
6
UAT
Business Testing & Sign-off
IT Led & Business Supported
Baseline Measures & Metrics, Business Definitions, KPI’s based on industry standards.
Definition
Notes: Identify Domain leads & teams

## Slide 13
October
November
December
January
Feb
March
April
May
June
Data Domains
Consumption Layers & Self Service
Project Genesis Plus – Schedule & Milestones
2022
2023
Requirements & Design
Master Data
Orders to Cash
Logistics
Procure to Pay
Finance
Hypercare
UAT
UAT
UAT
UAT
UAT
UAT
Product, Customer
Order Management, CRM, Sales Operations, EDI etc.
Sourcing, Distribution, Transportation
Supply Planning, Demand Planning, Procurement
AP, AR, GL, Accounting, Tax, Planning, Fixed Assets etc.
Notes: End of domain master data – you will get 1. Existing reports work

## Slide 14: Appendix

## Slide 15
v
Product
Backlog
Sprint Planning
Meeting
Daily
Stand-up
Scrum Master
Team
Product
Owner
Finished
Work
Sprint Review
+
Retrospective
Sprint
Backlog
Sprint
Every 2 weeks
Genesis Plus – Agile Project Methodology

## Slide 16: Genesis Plus - Risk Management Process

## Slide 17
Genesis Plus – Communication & Meetings Cadence
Meeting | Timing | Duration | Purpose | Audience
Project Kick-Off | Day One | 2 Hours | Align stakeholders and Project Team | Helen of Troy Business Stakeholders
Project Status Meeting | Monthly | 30 Minutes | Updates on tasks and project status | Helen of Troy Stakeholders
Daily Standup | Daily | 15 Minutes | Ensure progress is trending towards completing the committed work | Identified Helen of Troy contributors (optional)
Risk Management Meeting | Weekly | 30 Minutes | Identify Risks, Categorize Risk, Mitigation Plan | Project Team, Helen of Troy Stakeholders
Sprint Retrospective | Bi-weekly | 30 Minutes | Openly discuss the sprint and areas of improvement for upcoming sprints | Identified Helen of Troy contributors (optional)
Exec Steering Readouts | Monthly | ~60 Minutes | Share findings and demonstrate features as part of delivery | Helen of Troy Stakeholders and general business

## Slide 18: Thank You!

## Slide 19: Project Genesis – Scope & Goals
Implement Snowflake as the foundational data platform to process all internal (Oracle, Warehouse, Planning, DTC etc.), external (POS, Competition, Weather, etc.) data for enterprise analytics, and enable our business to self-serve using standard definitions, KPI’s, measures and metrics
MILESTONES
Phase 1
Implement the Snowflake data platform, replicate data between Oracle DW and Snowflake and switch all reporting to Snowflake
Phase 2
Reengineer data flows from source systems, and standardize terminology to enable self service
Team
Sponsor – Harish Ramani
PM – Gayle Isles, Balaji Srinivasan
IT – Information Delivery + 12 consultants
Business – DLC, All divisions / departments
Project Start
May 2022
Kick off
June 2022
Phase 1 Go-Live
Aug 2022
Phase 2 Start
Nov 2022
Project End
May 2023
Budget
Capex | Opex
844k | 350k

## Slide 20
Standard KPI’s, Definitions, & Measures
Drill down capability to drive actions
Divisional definitions, hierarchies, KPI’s that don’t align across HoT
~150 people within the business performing silo analytics at different parts of business
Business does not trust the data due to different terminologies and definitions
Only 3 people in IT build reports and dashboards for all of business
Current BI platform is not usable / intuitive for business self-service, adoption is difficult
Standards and governance need to be established for self-service
Current reports are either too high level or too detailed, driving actions need both at the same time
Lack of standard hierarchy impact ability to drill down from highest to lowest level
Business Self-Service
Project Genesis Plus –Problem Statement & Benefit Case
The current Oracle Data Platform is obsolete and cannot fulfill our vision to become a data driven organization. We also lack data governance across HoT at segment and brands to drive consistent action
Need to enable best in class data consumption tools like Power BI for easier self-service
Current platform performance also limits ability to drill down in reports
Prioritize HoT level metrics ex: for margins, working capital, turns, etc and drive consistent actions.

## Slide 21
Data Trust and Data Quality
New platform capabilities
Platform Reliability and Scalability
Project Genesis Plus –Problem Statement & Benefit Case
The current Oracle Data Platform is obsolete and cannot fulfill our vision to become a data driven organization. We also lack data governance across HoT at segment and brands to drive consistent action
Business does not trust the data due to lack of transparency in how / when data is processed
Lack of trust also due poor data quality driven by multiple definitions, hierarchies, terms across brands and divisions
Business and IT spend significant time in verifying data quality rather than using the data for decision making
Lack of QA environment in current platform leads to high rate of production defects
Lack of Disaster Recovery capability, these are available out of box in Snowflake
Instances of delayed reporting, and response time to load reports in current platform
Snowflake platform has an ecosystem of data providers that simplify data management
Ability to compress the time needed to build new data pipelines for analytical purposes
Ability to instant clone helps improve budget & forecast load accuracy, and validation
Ability for data sharing, to anonymize and monetize our data within the Snowflake ecosystem
Snowflake offers many of the box capabilities for us to be compliant with privacy regulations like GDPR, CCPA etc.

## Slide 22
ARA (Amazon Vendor Central ) Integration
Pegasus - SKU Rationalization
Market KPI Dashboard
Platform – Disaster Recovery, Platform Stability & scalability
Leverage Snowflake’s data ecosystem to rapidly build a scorecard to track macro economic indicators like CPI, CCI, Inflation, Interest rates, Unemployment, consumer debt etc from public data sources
Project Genesis Plus –Examples of Genesis benefits
The following are examples of completed or in-process activities that have a rapidly compressed timeline due to levering the capabilities within Genesis compared to our existing platform
Instant benefits due to Snowflake’s platorm include Disaster Recovery, instances of delayed reporting, improved reporting performance, and budget & forecast load accuracy, validation due to instant cloning
Within a week, we have built a data model that includes all data domains sales, forecasts, inventory, POS, to drive the SKU rationalization program as well as provide to our internal and external partners for self-service
Snowflake’s ecosystem allows us real-time access to Amazon Vendor Central info like PO, OTIF, Amazon’s forecasts, sell through, and inventory. This will help improve sales ops and planning for all our divisions @Amazon

## Slide 23
Chart: 
| Category 1 | Category 2 | Category 3
Capex | 363505 | 477675 | 2820
Committed
$363,505
Planned
$477,675
Not Planned
$2,820
Capex
844k
Chart: 
| Category 1 | Category 2 | Category 3
Capex | 169500 | 115000 | 65500
Committed
$169,500
Planned
$115,000
Not Planned
$65,500
Opex
350k
Project Genesis – FY23 Budget

## Slide 25
Enable the business to self-serve directly and immediately
Self-Service Needs
Identify issues at the highest level and drive actions at lowest level
Drill-down Capability
Implement Data Quality and increase trust in data
Data Trust
Define HoT standard definitions, metrics, & KPI’s
Definition / KPI’s
Scale our platform for performance, and different types of data
Scalability
Compress time to ingest and use new data ex: POS, Competition, Weather, etc.
External Data Integration
Project Genesis Plus –Problem Statement & Benefit Case
The current Oracle Data Platform is obsolete and cannot fulfill our vision to become a data driven organization.

## Slide 26
Current State
Future State
BU focused solutions, not aligned at HoT level
Differentiated process / data maintenance at each BU / department
Divisional definitions / hierarchies / KPI’s that don’t align across HoT
Difficult to access data needed to drive decisions.
Lack of adoption of reports / dashboards across the organization.
~150 analysts acting as shadow BI within the business maintaining own versions of BI solutions, reports, dashboards
Lack of Trust in Data
Usability challenges with Oracle Technology
Current platform is end of life, can't meet current and future needs
Collaborate and formalize standard definitions, measures, metrics, KPI’s, hierarchies, across HoT
Enable our associates to better manage the overall business by leveraging data.
Prioritize HoT level metrics ex: for margins, working capital, inventory turns, planning indicators, procurement etc and drive consistent actions.
Identify & Formalize “analyst” group to self-serve to scale the use of data across HoT
Build reports and dashboards that comply with CoE guidelines.
Establish, share best practices, standards and governance for CoE operation.
Enable best of breed consumption technologies like Power BI, & others
Project Genesis Plus –Problem Statement & Benefit Case