## Overall Work Progress
| Sub task | Sprint | Model Development resource | ODI SQL contact person | Peer Review | QA Testing | Start Date | End Date | Dependency | Status | Notes
Configuration and Setup | Get Dbt Admin/owner access | [8 empty] | Completed
| Dbt integration with Snowflake |  | Venkat | [6 empty] | Completed
| Dbt integration with Git |  | Venkat | [6 empty] | Completed
| Dbt Project creation |  | Venkat | [6 empty] | Completed
| Dbt Environment Setup |  | Aditya | [6 empty] | Completed
| Dbt finalize Models design for Data TL |  | Venkat & Aditya | [6 empty] | Completed
| Dbt Project configuration creation |  | Aditya | [6 empty] | Completed
| Dbt test run (model creation and end to end run) |  | Aditya | [6 empty] | Completed
| Dbt Baseline version |  | Venkat & Aditya | [6 empty] | Completed
| dbt unit testing guidelines |  | Aditya | [6 empty] | Completed
| ci/cd process guidelines |  | Gurpreet | [6 empty] | In Progress | dbt uses github merge process. Snowflake CICD using schemachane is in Testing
Pipeline Development | Audit Macros Development |  | Aditya | [6 empty] | Completed
| Delta Macros Development |  | Aditya | [6 empty] | Completed
| Job Execution with Tags |  | Venkat | [6 empty] | Completed
| Incremental - Full refresh customization |  | Aditya | [6 empty] | Completed
| Snapshot - Customization |  | Venkat | [6 empty] | In Progress
| ETL PROC WID job/env variable setup |  | Gurpreet | [6 empty] | Completed
| Global Master data - Generate Staging Models |  | Venkat | [6 empty] | Completed
| W_INT_ORG_D |  | Pradhnya | venkat | [5 empty] | Completed
| W_INVENTORY_PRODUCT_D |  | Aditya & venkat | venkat | [5 empty] | In Progress
| W_XACT_SOURCE_D |  | Pradhnya | venkat | [5 empty] | Completed, Peer review pending
| W_DAY_D |  | Bala | venkat
| W_XACT_TYPE_D |  | Gurpreet | srinivas-Done |  |  |  |  | W_XACT_TYPE_DS W_USER_D | In Progress
| W_STATUS_D |  | Pradhnya | srinivas-Done | [5 empty] | To be discussed with Venkat
| W_CUSTOMER_ACCOUNT_D |  | Bala | venkat | [5 empty] | In Progress
| W_CUSTOMER_LOC_D |  | Ambika | srinivas-Done
| W_CUSTOMER_LOC_USE_D |  |  | srinivas-Table Empty in oracle
| W_EMPLOYEE_D |  | Ambika | srinivas-Done
| W_USER_D |  | Gurpreet | srinivas-Done | [5 empty] | In Progress
| W_SUPPLIER_ACCOUNT_D |  | Pradhnya | srinivas-Done | [5 empty] | In Progress
| W_TERRITORY_D |  | Abhishek | venkat
| W_MCAL_PERIOD_D |  |  | srinivas-Done
| W_LEDGER_D |  | Gurpreet | venkat | [5 empty] | Completed, Peer review pending
WC_AVG_EXCH_RATE_G
| W_FREIGHT_TERMS_D |  | Abhishek | Kalaivani | [5 empty] | Completed, Peer review pending
| Financials - Generate Staging Models |  | venkat
| W_PAYMENT_METHOD_D |  |  | Kalaivani
| W_GL_ACCOUNT_D |  |  | Kalaivani
| W_GL_SEGMENT_D |  |  | Kalaivani
| W_GL_SEGMENT_DH |  |  | srinivas
| W_PAYMENT_TERMS_D |  |  | srinivas
| W_AR_AGING_BUCKETS_D |  |  | srinivas
| W_AP_TERMS_D |  |  | srinivas
| WC_FUND_D |  |  | Kalaivani
| W_SLA_XACT_F |  |  | venkat
| W_AR_XACT_F |  |  | srinivas
| W_AP_XACT_F |  |  | Kalaivani
| W_AR_AGING_INVOICE_A |  |  | srinivas
| W_AP_AGING_INVOICE_A |  |  | srinivas
| W_GL_BALANCE_F |  |  | Kalaivani
| WC_HYPERION_BUDGET_F |  |  | venkat
| WC_TRADE_BALANCES_F |  |  | Kalaivani
| WC_TRADE_FUNDS_F |  |  | Kalaivani
| WC_CLAIMS_F |  |  | Kalaivani
W_FIXED_ASSET_D
W_ASSET_BOOK_D
W_ASSET_CATEGORY_D
W_ASSET_LOCATION_D
W_FA_BALANCE_F
W_FA_XACT_F
| WC_SHARE_DETAILS_F |  |  | venkat
| Supply Chain - Generate Staging Models |  | Venkat
| W_BUSN_LOCATION_D |  |  | srinivas
| WC_CUSTOMER_ITEMS_D |  |  | venkat
| W_INVENTORY_DAILY_BAL_F |  |  | Kalaivani
| W_SALES_CYCLE_LINE_F |  |  | venkat
| WC_DM_FORECAST_F |  |  | Kalaivani
| WC_DAILY_DOLLAR_OPEN_ORDERS_F |  |  | venkat
| WC_PLANNED_ORDERS_F |  |  | srinivas
| WC_SALES_DEMAND_F |  |  | srinivas
| WC_ASCP_FISC_PERIOD_DRYBAR_F |  |  | srinivas
| WC_ASCP_FISC_PERIOD_SUMMARY_F |  |  | srinivas
| WC_ASCP_WEEKLY_SUMMARY_F |  |  | srinivas
| WC_PRICING_LIST_F |  |  | kalaivani
| W_SALES_INVOICE_LINE_F |  |  | kalaivani
| W_SALES_PICK_LINE_F |  |  | venkat
| W_PRODUCT_LOT_XACT_F |  |  | srinivas
| W_PURCH_SCHEDULE_LINE_F |  |  | srinivas
| W_PURCH_RCPT_F |  |  | srinivas
| W_PURCH_RQSTN_LINE_F |  |  | srinivas
WC_KPI_SEGMENTS_D
| WC_OTIF_SCORECARD_F |  |  | kalaivani
| WC_PURCHASE_DISTRIBUTIONS_F |  |  | kalaivani
Semantic layer models
WC_CUSTOMER_NET_SALES_A
WC_GL_OTHER_A
WC_INVENTORY_RESERVES_A

## Development Steps
| post all ODI sqls to folder GenesisPlus - General\Data Engineering\Data Transformation\ODI SQL Transformations | simple | medium | complex
Step 1: | Get all SDE sqls from contact person (column D from overall work progress sheet) for a given table |  |  |  | get both SDE and SIL queries SDE queries should be used for the development of dbt models. SIL query can be used for reference for some missing columns information from SDE
Step 2: | get target table definition from PROD_EDW.BI11g_DW schema (column names and data types and add to excel)
Step 3: | Create mapping document from SDE query select clause columns to Target columns |  | done |  | for examples, refer a few in GenesisPlus - General\Data Engineering\Data Transformation\SQL to Target Table Mappings
Step 4: | Communicate the contact person from step 1, for any missing column mappings |  | done
Step 5: | ODI contact person should either update the column formula if missing or make it as ignore if no value is mapped |  | done
Step 6: | In parallel, developer can start analyzing SDE sqls, create feature branch from Develop branch 1. Get the missing source tables replicated from Matillion 2. Identify transformation rules which can be moved to staging views as per data architecture and make changes to staging views 3. Identify if any query constructs can be moved to Intermediate layer and create models for intermediate 4. Identify where clause construct for delta logic |  | done
Step 7: | Create load model and corresponding config file |  | done
Step 8: | Unit Testing and documenting Test results |  | DONE
Step 9: | Create pull request and set reviewer |  | final code to be done
Step 10: | Reviewer checks and give feedback and changes are retested if any and reviewed |  | in progress
If code review is passed then merge the changes to develop branch
General guidelines on models refactoring
1 | staging view naming convention as stg_oracle__(plural entity name). mostly remove prefixes lize hz, oe, wsh etc.. which are schema prefixes in the source table in ODS |  | done |  | this can be corrected during peer review
2 | config section should have a) integration_id for dimension tables: to_char(primary_key) ¦¦'~'¦¦to_char(_source_id) b) for w_inventory_product_d: to_char(inventory_item_id)¦¦'~'¦¦to_char(organization_id)¦¦'~Y' c) merge_exclude_columns: W_INSERT_DATE, DELTE_FLAG and based on context if any d) tag value: master_data, financials |  |  |  | hashkey are not used as we did not see any performance gain compared to varchar joins (integration_id) and did not see an immediate surrogate key use
3 | For Fact tables add corresponding IDs like customer_id: to_char(customer_account_id)¦¦'~'¦¦to_char(_source_id) for inventory_product_id it will be to_char(inventory_item_id)¦¦'~'¦¦to_char(organization_id)¦¦'~'¦¦to_char(_source_id) if organization_id/warehouse_id/shipping_org_id is not available then use 82 (which is GLO org)
4 | w_insert_date, w_update_date takes $batch_start_time, Delete_flag = 'N' |  | no
5 | etl_proc_id takes environment variable env_var(etl_proc_id) |  | done
6 | for some targe column name start with X_, remove the prefix X_ |  | done | x_addresse
7 | ignore all columns listed from proc call edw_metadata.u_get_null_columns_list('W_FREIGHT_TERMS_D','PROD_EDW','BI11G_DW','100');
8 | Mapping document should have 4 columns (Target Column Name, source Table Name, Source Column Name) rest you can add any notes, remarks etcc which helps for development |  | done
9 | git development branch name (initials_model_name) |  | done
10 | ignore src_effective_from,to and effective_from,to dates and current flag from all tables (except w_inventory_product_d) |  | done
11 | Aux_ date columns is to track delta tables other than primary table if identifying delta from primary table, and also other auxilary tables like table a or table b then primary table chaged_on_dt goes to last_update_date, table a and table b changed_on_dt goes to Aux1 and Aux2 dates remove extra aux date columns |  | done
12 | UTR should contain rows matching criteria (Audit table will track snowflake response of changed rows into Audit table). this number should match to rows extracted from source and rows affected in the target table execute corresponding queries to get the row counts and match to audit log table entry
13 | use ansi-joins (particulary avoid (+) notation in non-ansi joins) to be consistant and migration friendly. |  |  |  | https://community.snowflake.com/s/article/Performance-Implications-of-using-Non-ANSI-syntax-versus-ANSI-join-syntax
14 | update work progress sheet, that if any columns are quoted with static values like "NULL" as place holder for post sql updates depending on fact tables
15 | from Mapping if you see 'Not_Applicable', '_unassigned' kind of values ignore those coalesce functions and just map source column
16 | as surrogate keys are not maintained, follow as mentioned below a) ignore/drop ROW_WID, SCD1_WID columns in the target table b) Rest all other _WIDs, rename to _ID c) for these renamed _ID columns populate values as source_column ¦¦'~'¦¦_source_id example: CHANGED_BY_WID -> rename to CHANGED_BY_ID (value looks like 1117890~100 ) LEDGER_WID -> rename to LEDGER_ID |  | done
17 | below columns are warehouse specific columns and should not be in staging views delete_flg, integration_id, datasource_num_id, w_insert_dt, w_update_dt |  | done

## Sheet1
|  | gurpree | bala | pradhnya | abishek | ambhika | venkat | avg
analysis | simple | 4 | 5 | 3 | 2
| medium | 12 | 10 | 6 | 7
| complex | 16 | 15 | 9 | 10
develop
| simple | 4 | 10 | 24 | 10 | 10
| medium | 12 | 25 | 48 | 30 | 30
| complex | 24 | 40 | 72 | 50 | 50
Peer Review | simple | 2 | 2 | 5 | 4 | 2 | 2
| medium | 6 | 5 | 10 | 9 | 4 | 4
| complex | 10 | 7 | 15 | 18 | 8 | 6
QA | simple
medium
complex
2
Deploy | simple
medium
complex

## Model Level plan
Subject Area | Module | Model | Model Type | Start Date | End Date | Resource | Status
Global | Master Data | W_CUSTOMER_ACCOUNT_D | Base | 2022-11-01 | 2022-11-01 | SE1
Global | Master Data | W_CUSTOMER_ACCOUNT_D | Stage | 2022-11-01 | 2022-11-02 | SE1
Global | Master Data | W_CUSTOMER_ACCOUNT_D | Integration | 2022-11-02 | 2022-11-03 | SE1
Global | Master Data | W_CUSTOMER_ACCOUNT_D | Load | 2022-11-04 | 2022-11-07 | SE1
Testing | Master Data | W_CUSTOMER_ACCOUNT_D | System | 2022-11-08 | 2022-11-09 | SE1
Devops | Master Data | W_CUSTOMER_ACCOUNT_D | Test Promotion | 2022-11-10 | 2022-11-10 | SE1
Global | Master Data | W_INVENTORY_PRODUCT_D | Base | 2022-11-01 | 2022-11-01 | SE2
Global | Master Data | W_INVENTORY_PRODUCT_D | Stage | 2022-11-01 | 2022-11-02 | SE2
Global | Master Data | W_INVENTORY_PRODUCT_D | Integration | 2022-11-02 | 2022-11-04 | SE2
Global | Master Data | W_INVENTORY_PRODUCT_D | Load | 2022-11-07 | 2022-11-08 | SE2
Testing | Master Data | W_INVENTORY_PRODUCT_D | System | 2022-11-09 | 2022-11-09 | SE2
Devops | Master Data | W_INVENTORY_PRODUCT_D | Test Promotion | 2022-11-10 | 2022-11-10 | SE2
Global | Master Data | W_EMPLOYEE_D | base | 2022-11-01 | 2022-11-01 | DE1
Global | Master Data | W_EMPLOYEE_D | Stage | 2022-11-01 | 2022-11-02 | DE1
Global | Master Data | W_EMPLOYEE_D | Integration | 2022-11-03 | 2022-11-04 | DE1
Global | Master Data | W_EMPLOYEE_D | Load | 2002-11-04 | 2022-11-07 | DE1
Global | Master Data | W_STATUS_D | Stage | 2022-11-01 | 2022-11-01 | DE4
Global | Master Data | W_STATUS_D | Load | 2022-11-02 | 2022-11-02 | DE4
Global | Master Data | W_XACT_SOURCE_D | stage | 2022-11-01 | 2022-11-01 | DE3
Global | Master Data | W_XACT_SOURCE_D | Integration | 2022-11-02 | 2022-11-02 | DE3
Global | Master Data | W_XACT_SOURCE_D | Load | 2022-11-03 | 2023-11-03 | DE3
Global | Master Data | W_CUST_LOC_USE_D | stage | 2022-11-04 | 2022-11-04 | DE3
Global | Master Data | W_CUST_LOC_USE_D | Load | 2022-11-07 | 2022-11-07 | DE3
Global | Master Data | W_CUSTOMER_LOC_D | stage | 2022-11-01 | 2022-11-01 | DE2
Global | Master Data | W_CUSTOMER_LOC_D | Integration | 2022-11-02 | 2022-11-03 | DE2
Global | Master Data | W_CUSTOMER_LOC_D | Load | 2022-11-04 | 2022-11-07 | DE2
Global | Master Data | W_SUPPLIER_ACCOUNT_D | stage | 2022-11-03 | 2022-11-03 | DE4
Global | Master Data | W_SUPPLIER_ACCOUNT_D | Integration | 2022-11-04 | 2022-11-04 | DE4
Global | Master Data | W_SUPPLIER_ACCOUNT_D | Load | 2022-11-07 | 2022-11-07 | DE4
Global | Master Data | W_MCAL_PERIOD_D | stage | 2022-11-11 | 2022-11-11 | SE1
Global | Master Data | W_MCAL_PERIOD_D | integration | 2022-11-11 | 2022-11-14 | SE1
Global | Master Data | W_MCAL_PERIOD_D | load | 2022-11-15 | 2022-11-15 | SE1
Global | Master Data | W_DAY_D | stage | 2022-11-16 | 2022-11-17 | SE1
Global | Master Data | W_DAY_D | integration | 2022-11-17 | 2022-11-18 | SE1
Global | Master Data | W_DAY_D | Load | 2022-11-21 | 2022-11-22 | SE1
Global | Master Data | W_TERR_D | stage | 2022-11-11 | 2022-11-11 | SE2
Global | Master Data | W_TERR_D | integration | 2022-11-14 | 2022-11-16 | SE2
Global | Master Data | W_TERR_D | load | 2022-11-16 | 2022-11-17 | SE2
Global | Master Data | W_INT_ORG_D | Stage | 2022-11-08 | 2022-11-09 | DE1
Global | Master Data | W_INT_ORG_D | Integration | 2022-11-09 | 2022-11-11 | DE1
Global | Master Data | W_INT_ORG_D | Load | 2022-11-11 | 2022-11-14 | DE1
Global | Master Data | W_USER_D | load | 2022-11-08 | 2022-11-08 | DE3
Global | Master Data | W_XACT_TYPE_D | base | 2022-11-08 | 2022-11-08 | DE2
Global | Master Data | W_XACT_TYPE_D | stage | 2022-11-09 | 2022-11-10 | DE2
Global | Master Data | W_XACT_TYPE_D | integration | 2022-11-10 | 2022-11-14 | DE2
Global | Master Data | W_XACT_TYPE_D | load | 2022-11-15 | 2022-11-17 | DE2
Financials | Master Data | W_PAYMENT_METHOD | Stage | 2022-11-09 | 2022-11-09 | DE3
Financials | Master Data | W_PAYMENT_METHOD | Integration | 2022-11-10 | 2022-11-10 | DE3
Financials | Master Data | W_PAYMENT_METHOD | load | 2022-11-11 | 2022-11-11 | DE3
Financials | Master Data | W_LEDGER_D | stage | 2022-11-14 | 2022-11-14 | DE3
Financials | Master Data | W_LEDGER_D | load | 2022-11-14 | 2022-11-14 | DE3
Financials | Master Data | W_PAYMENT_TERMS_D | stage | 2022-11-08 | 2022-11-08 | DE4
Financials | Master Data | W_PAYMENT_TERMS_D | Integration | 2022-11-08 | 2022-11-09 | DE4
Financials | Master Data | W_PAYMENT_TERMS_D | load | 2022-11-09 | 2022-11-09 | DE4
Financials | Master Data | W_GL_SEGMENT_D | base | 2022-11-10 | 2022-11-10 | DE4 |  | A
Financials | Master Data | W_GL_SEGMENT_D | Stage | 2022-11-10 | 2022-11-11 | DE4
Financials | Master Data | W_GL_SEGMENT_D | Integration | 2022-11-11 | 2022-11-14 | DE4
Financials | Master Data | W_GL_SEGMENT_D | Load | 2022-11-14 | 2022-11-14 | DE4
Financials | Master Data | W_GL_SEGMENT_DH | base | 2022-11-18 | 2022-11-18 | SE2 |  | A
Financials | Master Data | W_GL_SEGMENT_DH | stage | 2022-11-18 | 2022-11-19 | SE2
Financials | Master Data | W_GL_SEGMENT_DH | Integration | 2022-11-19 | 2022-11-20 | SE2
Financials | Master Data | W_GL_SEGMENT_DH | Load | 2022-11-18 | 2022-11-18 | SE2
Financials | Master Data | W_GL_ACCOUNT_D